## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Product Backlog
| Table 1 | Product Backlog
Sprint Backlog
| Table 1 | Sprint Backlog
Stand up Meeting
| Table 1 | Stand up Meeting
Retrospection
| Table 1 | Retrospection

## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-001 | Study startup validation frameworks, multi-agent design patterns, and web search API integration. | Must Have | None | Entire Team | 3- Completed
Sprint 1 | Sprint 1 | US-002 | Design system architecture, agent roles, orchestration flow, and data models. | Must Have | US-001 | Vijayaragavan | 3- Completed
Sprint 1 | Sprint 1 | US-003 | Develop startup idea submission interface and structured idea extraction using LLM. | Must Have | US-001 | Afik Esmal | 3- Completed
Sprint 1 | Sprint 1 | US-004 | Integrate Web Search Agent using Tavily API or equivalent for live market and competitor data retrieval. | Must Have | US-001,US-003 | Afik Esmal | 3- Completed
Sprint 2 | Sprint 2 | US-005 | Develop Market Opportunity and Customer Segmentation Analysis Agent — evaluates industry size, trends, and target segments. | Must Have | US-004 | Jananipriyadharshini | 3- Completed
Sprint 2 | Sprint 2 | US-006 | Build Competitor Discovery and Comparison Agent — identifies existing players, compares offerings, and highlights gaps. | Must Have | US-004 | Afik Esmal | 3- Completed
Sprint 2 | Sprint 2 | US-007 | Implement agent orchestration — ensure sequential pipeline execution with context passing between agents. | Must Have | US-004,US-005,US-006 | Entire Team | 3- Completed
Sprint 2 | Sprint 2 | US-008 | Validate market and competitor outputs using sample startup ideas across different domains. | Must Have | US-007 | Entire Team | 3- Completed
Sprint 3 | Sprint 3 | US-009 | Develop SWOT + Risk Analysis Agent. | Must Have | US-007 | Vijayaragavan | 3- Completed
Sprint 3 | Sprint 3 | US-010 | Complete remaining agent integration and context passing across the multi-agent workflow. | Must Have | US-005,US-006,US-007,US-009 | Entire Team | 3- Completed
Sprint 3 | Sprint 3 | US-011 | Validate integrated agent outputs and fix agent execution errors. | Must Have | US-010 | Entire Team | 3- Completed
Sprint 3 | Sprint 3 | US-012 | Test the system using sample startup ideas across different domains. | Must Have | US-011 | Entire Team | 3- Completed
Sprint 4 | Sprint 4 | US-013 | Complete final system integration and bug fixing. | Must Have | US-010,US-011 | Entire Team | 3- Completed
Sprint 4 | Sprint 4 | US-014 | Refine frontend UX and visualization and prepare the deployment. | Must Have | US-013 | Afik Esmal | 3- Completed
Sprint 4 | Sprint 4 | US-015 | Complete Agile documentation, GitHub finalization, and permanent deployment testing. | Must Have | US-013,US-014 | Entire Team | 3- Completed
Sprint 4 | Sprint 4 | US-016 | Prepare and deliver final live presentation and project demonstration. | Must Have | US-015 | Entire Team | 3- Completed
Note on F1: : ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 176 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | T-001 | Study startup validation frameworks and multi-agent design patterns | 2026-07-01 | 2026-07-14 | Entire Team | Research | 3- Completed | 8 | bar: Day 1 to Day 8
US-001 | T-002 | Study Web Search API integration requirements | 2026-07-01 | 2026-07-14 | Afik Esmal | Research | 3- Completed | 8 | bar: Day 1 to Day 8
US-002 | T-003 | Design system architecture, agent roles and data models | 2026-07-01 | 2026-07-14 | Vijayaragavan | Design | 3- Completed | 8 | bar: Day 1 to Day 8
US-002 | T-004 | Design MAS workflow and framework justification | 2026-07-01 | 2026-07-14 | Jananipriyadharshini | Design | 3- Completed | 8 | bar: Day 1 to Day 8
US-003 | T-005 | Develop startup idea submission interface | 2026-07-01 | 2026-07-14 | Afik Esmal | Build | 3- Completed | 8 | bar: Day 1 to Day 8
US-003 | T-006 | Implement structured idea extraction using LLM | 2026-07-01 | Build | Afik Esmal | Coding | 3- Completed | 8 | bar: Day 1 to Day 8
US-004 | T-007 | Research and integrate Tavily Web Search API | 2026-07-01 | Build | Afik Esmal | Coding | 3- Completed | 8 | bar: Day 1 to Day 8
US-004 | T-008 | Define search evidence and structured output handling | 2026-07-01 | Build | Bhargavi | Design | 3- Completed | 8 | bar: Day 1 to Day 8
SPRINT 2 BACKLOG
US-005 | T-009 | Develop Market Opportunity Agent (Industry Analysis) | 2026-07-15 | Build | Bhargavi | Build | 2- In Progress | 8 | bar: Day 1 to Day 8
US-006 | T-010 | Develop Competitor Discovery Agent (Rival Identification) | 2026-07-15 | Build | Afik Esmal | Build | 3- Completed | 8 | bar: Day 1 to Day 8
US-006 | T-011 | Identify direct and indirect competitors | 2026-07-15 | 2026-07-28 | Afik Esmal | Analysis | 3- Completed | 8 | bar: Day 1 to Day 8
US-007 | T-012 | Develop Comparison Agent (Competitor Comparison) | 2026-07-15 | 2026-07-28 | Vijayaragavan | Build | 3- Completed | 8 | bar: Day 1 to Day 8
US-007 | T-013 | Implement sequential agent orchestration and context passing | 2026-07-15 | 2026-07-28 | Entire Team | Coding | 2- In Progress | 8 | bar: Day 1 to Day 8
US-008 | T-014 | Validate market and competitor outputs with sample startup ideas | 2026-07-15 | 2026-07-28 | Entire Team | Testing | 3- Completed | 8 | bar: Day 1 to Day 8
SPRINT 3 BACKLOG
US-009 | T-015 | Develop SWOT + Risk Analysis Agent | 2026-07-29 | 2026-08-11 | Vijayaragavan | Build | 3- Completed | 8 | bar: Day 1 to Day 8
US-010 | T-016 | Complete remaining agent integration and context propagation | 2026-07-29 | 2026-08-11 | Entire Team | Integration | 3- Completed | 8 | bar: Day 1 to Day 8
US-011 | T-017 | Fix agent execution errors and improve local testing | 2026-07-29 | 2026-08-11 | Entire Team | Debugging | 3- Completed | 8 | bar: Day 1 to Day 8
US-012 | T-018 | Validate the integrated pipeline across sample startup ideas | 2026-07-29 | 2026-08-11 | Entire Team | Testing | 3- Completed | 8 | bar: Day 1 to Day 8
SPRINT 4 BACKLOG
US-013 | T-019 | Complete final multi-agent integration and bug fixing | 2026-08-12 | 2026-08-25 | Entire Team | Integration | 3- Completed | 8 | bar: Day 1 to Day 8
US-014 | T-020 | Refine frontend UX, visualization and user flow | 2026-08-12 | 2026-08-25 | Afik Esmal | Build | 3- Completed | 8 | bar: Day 1 to Day 8
US-015 | T-021 | Complete Agile documentation, GitHub finalization and deployment testing | 2026-08-12 | 2026-08-25 | Entire Team | Documentation | 3- Completed | 8 | bar: Day 1 to Day 8
US-016 | T-022 | Prepare final presentation, demo and live project walkthrough | 2026-08-12 | 2026-08-25 | Entire Team | Presentation | 3- Completed | 8 | bar: Day 1 to Day 8
Note on D2: : ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: : ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: : ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: : ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: : ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: : ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: : ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: : ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: : ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: : ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: : ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: : ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: : ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: : ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: : ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: : ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: : ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Week 1 | None | Team discussed roles, Web Search Agent purpose, architecture, framework selection and MAS workflow.
Sprint 1 | Week 1 | Initial uncertainty about Web Search Agent and Draw.io | Team researched the agent concept and began architecture and flow design.
Sprint 1 | Week 2 | Minor API integration/debugging issues | Afik continued frontend/backend work and Tavily integration; team reviewed outputs.
Sprint 1 | Week 2 | Presentation coordination and teammate availability | Completed recordings, integrated the presentation and submitted Milestone 1 video.
Sprint 2 | Week 3 | Market Opportunity Agent work pending | Bhargavi continued the Market Opportunity Agent and researched data sources.
Sprint 2 | Week 3 | Agent integration dependencies | Team divided Market Opportunity, Customer Segmentation, Competitor Discovery and Comparison tasks.
Sprint 2 | Week 4 | Customer agent errors during local testing | Jananipriyadharshini continued debugging and prepared the Customer Segmentation Agent for integration.
Sprint 2 | Week 4 | Delayed work and presentation scheduling | Requested an extension and coordinated integration and presentation readiness.
Sprint 3 | Week 5 | Agent integration/context-passing issues | Team integrated remaining agents, fixed execution errors and tested the sequential workflow.
Sprint 3 | Week 5 | Local testing/debugging | Re-tested agent outputs and corrected errors before broader validation.
Sprint 3 | Week 6 | Validation across different startup ideas | Ran sample startup ideas through the pipeline and reviewed outputs.
Sprint 3 | Week 6 | Coordination for final integration | Team reviewed progress and prepared the project for final stabilization.
Sprint 4 | Week 7 | Deployment issues with temporary link | Temporary deployment was replaced with a permanent deployment after bug fixing.
Sprint 4 | Week 7 | Frontend and integration bugs | Afik fixed issues, refined the UX and asked teammates to test all agents.
Sprint 4 | Week 8 | Documentation and presentation preparation | Completed Agile/documentation updates, finalized GitHub work and coordinated the final demo.
Sprint 4 | Week 8 | Final presentation coordination | Prepared slides, demo flow and a pre-presentation team meeting.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-07-01 | 2026-07-14 | Entire Team | Start agent planning earlier. | Avoid waiting until presentation time for recordings. | Continue architecture, research, frontend work and GitHub collaboration. | Architecture, MAS workflow, Tavily research, frontend and Milestone 1 presentation completed.
2 | Sprint 2 | 2026-07-15 | 2026-07-28 | Entire Team | Start integration testing earlier. | Avoid delaying dependent agent work. | Continue task division, agent development, GitHub collaboration and testing. | Competitor Discovery, Customer Segmentation and Comparison progressed; Market Opportunity remained delayed/in progress.
3 | Sprint 3 | 2026-07-29 | 2026-08-11 | Entire Team | Start end-to-end testing earlier and track dependencies. | Avoid late debugging and dependency bottlenecks. | Continue orchestration, context passing and collaborative debugging. | SWOT + Risk Analysis, remaining integration, validation and agent-error fixing completed.
4 | Sprint 4 | 2026-08-12 | 2026-08-25 | Entire Team | Start deployment validation and presentation preparation earlier. | Avoid relying on temporary deployment links near presentation. | Continue UX refinement, GitHub collaboration, testing and team coordination. | Final integration, bug fixing, deployment, documentation, final testing and presentation/demo preparation completed.